## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Mentor (Code Review) | 2026-07-10 | days_span() counted Saturdays and Sundays, over-counting the working days deducted for a leave request. | Sprint 1 | Sai Lakshmi | Logical | Reworked days_span() to iterate the range and skip weekends; added regression test. | 2026-07-11 | Closed | Guarded by test_days_span_excludes_weekends.
2 | Sai Lakshmi | 2026-07-10 | A reversed date range (end date before start date) produced a negative day count. | Sprint 1 | Sai Lakshmi | Logical | days_span() now returns 0 for invalid/reversed ranges. | 2026-07-11 | Closed | Guarded by test_days_span_invalid_range_is_zero.
3 | Sai Lakshmi | 2026-07-12 | Requesting an unsupported leave type (e.g. 'sabbatical') raised a KeyError and aborted the PolicyAgent. | Sprint 1 | Sai Lakshmi | Logical | Unknown types now fail safe: manager_required=True with a 'No policy found' note. | 2026-07-12 | Closed | Guarded by test_policy_agent_unknown_type_flags_manager_review.
4 | Mentor (Code Review) | 2026-07-16 | 'db_path' was exposed as a model-controllable tool argument, breaking least-privilege (model could point tools at any DB file). | Sprint 2 | Sai Lakshmi | Standards | Removed db_path from all tool schemas; write tools kept behind trusted agents only. | 2026-07-17 | Closed | Security / least-privilege. Guarded by test_read_tools_have_schemas.
5 | Sai Lakshmi | 2026-07-17 | When an enterprise tool was unreachable, the raised ConnectionError propagated and crashed the whole tool-calling loop. | Sprint 2 | Sai Lakshmi | Logical | Tool errors are now caught, recorded, and fed back to the model so the loop continues. | 2026-07-18 | Closed | Graceful degradation. Guarded by test_failing_tool_is_recorded_not_raised.
6 | Sai Lakshmi | 2026-07-18 | If the model requested a tool that was never offered, the loop crashed with a lookup error. | Sprint 2 | Sai Lakshmi | Logical | Unknown-tool calls are rejected with an 'unknown tool' message; the model recovers and retries a valid tool. | 2026-07-18 | Closed | Guarded by test_unknown_tool_call_is_rejected_gracefully.
7 | Sai Lakshmi | 2026-07-18 | The tool-calling loop could run indefinitely when the model repeatedly called the same tool without answering. | Sprint 2 | Sai Lakshmi | Logical | Bounded the loop with max_iterations; loop marks itself 'exhausted' when the cap is hit. | 2026-07-19 | Closed | Guarded by test_runaway_loop_is_bounded.
8 | Sai Lakshmi | 2026-07-19 | When the model skipped its tools entirely, agent state was left empty and downstream agents failed. | Sprint 2 | Sai Lakshmi | Logical | Agents now fall back to direct tool calls when the model returns no tool calls. | 2026-07-19 | Closed | Guarded by test_agent_survives_model_that_never_calls_tools.
9 | Sai Lakshmi | 2026-07-20 | Holiday calendar connector mishandled range boundaries, occasionally excluding a holiday on the exact start/end date. | Sprint 2 | Sai Lakshmi | Logical | Fixed inclusive date-range filtering in holidays_between(). | 2026-07-20 | Closed | Guarded by test_connector_filters_by_range.
10 | Mentor (Code Review) | 2026-07-28 | Long-term memory stats reported the wrong last_outcome because history was not ordered newest-first. | Sprint 3 | Sai Lakshmi | Logical | History query now orders records newest-first; stats derive last_outcome from the first row. | 2026-07-29 | Closed | Guarded by test_long_term_memory_stats.
11 | Sai Lakshmi | 2026-07-30 | An escalated request did not update its status to AWAITING_MANAGER; it stayed COMPLETED. | Sprint 3 | Sai Lakshmi | Logical | Notification/Decision now set the request status to match the outcome (AWAITING_MANAGER on escalate). | 2026-07-30 | Closed | Guarded by test_escalate_path_manager_required.
12 | Mentor (Code Review) | 2026-08-02 | Re-submitting a request with identical dates silently escalates as an overlap, confusing first-time demo users. | Sprint 3 | Sai Lakshmi | Others | By design (duplicate/overlap detection). Documented 'run --init-db before demos' in README. | 2026-08-02 | Closed | Documentation fix, not a code change.
13 | Sai Lakshmi | 2026-08-04 | CLI prints the raw balance dict instead of a formatted, human-readable summary line. | Sprint 3 | Sai Lakshmi | User Interface | Cosmetic formatting improvement planned for the CLI output layer. |  | Open | Low priority / cosmetic.
14 | Mentor (Code Review) | 2026-08-05 | Pipeline orchestration is sequential; the planned LangGraph-based orchestrator is not yet implemented. | Sprint 3 | Sai Lakshmi | Maintainability | Tracked as a follow-up enhancement; sequential pipeline is functionally complete. |  | Open | Tech-debt / enhancement noted in README.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others